## RACI Matrix
RACI MATRIX TEMPLATE | [5 empty] | https://bit.ly/342gPlv
PROJECT TITLE | [8 empty] | PROJECT MANAGER
Mission to Complete the Thing We Need to Do | [8 empty] | Alia
|  | R | A | C | I
READY TO START? | TASK DESCRIPTION | RESPONSIBLE | ACCOUNTABLE | CONSULTED | INFORMED | % of PROGRESS | DUE DATE | STATUS | NOTES | READY TO START? | STATUS
Yes | INITIATE PHASE ACTIVITIES |  |  |  |  | 38.75% |  | In Progress |  | Yes | Not Started
Yes | Request Review by PMO | Alia |  | Rachel | Ian + Carl | 80% |  | Needs Review |  | No | In Progress
No | Submit Project Request | Alia |  | Rachel | Ian + Carl | 50% |  | In Progress |  |  | Complete
Yes | Research Solution |  | Rachel | Ian + Carl | Alia | 20% |  | Needs Review |  |  | Needs Review
No | Develop Business Case | Rachel | Alia | Carl | Ian | 5% |  | Overdue |  |  | Overdue
Yes | PLAN PHASE ACTIVITIES |  |  |  |  | 33.33% |  | On Hold |  |  | On Hold
Yes | Create Project Charter | Ian | Rachel | Carl | Alia | 100% |  | Complete
No | Create Schedule | Carl | Rachel |  | Alia | 0% |  | Not Started
No | Create Additional Plans as Required | Carl | Rachel + Ian | Alia |  | 0% |  | On Hold
No | EXECUTE PHASE ACTIVITIES |  |  |  |  | 0%
No | Build Deliverables |  |  |  |  | 0%
No | Create Status Report |  |  |  |  | 0%
No | CONTROL PHASE ACTIVITIES |  |  |  |  | 0%
No | Perform Change Management |  |  |  |  | 0%
No | CLOSE PHASE ACTIVITIES |  |  |  |  | 0%
No | Create Lessons Learned |  |  |  |  | 0%
No | Create Project Closure Report |  |  |  |  | 0%

## BLANK RACI Matrix
RACI MATRIX TEMPLATE
PROJECT TITLE | [8 empty] | PROJECT MANAGER
|  | R | A | C | I
READY TO START? | TASK DESCRIPTION | RESPONSIBLE | ACCOUNTABLE | CONSULTED | INFORMED | % of PROGRESS | DUE DATE | STATUS | NOTES | READY TO START? | STATUS
[10 empty] | Yes | Not Started
[10 empty] | No | In Progress
Complete
Needs Review
Overdue
On Hold

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.