## Lessons Learned
Get Access to our Complete Collection of 40 Editable Google Doc/Sheet Lessons Learned Templates here.
Lessons Learned
| Project name: |  |  |  | Project number:
| Project manager: |  |  |  | Project sponsor:
[Text in green and enclosed in [ ] is explanatory example test and should be deleted]
| ID | Date raised | Event (what happened) | Lesson category | Early warning signs? | Recommendations | Action(s) | Owner | WBS ID | Status
| [1] | [mm/dd/yyyy] | [Give a clear detailed description of what happened and the impact. Lessons can be positive as well as negative]. | [Positive / negative / | [Note any warning signs that could be picked up in future] | [Recommendation for improvement or to remove the issue for future projects]. | [Actions that will be taken to implement the lesson learned] | [Person who will take the action(s)] | [Link to WBS ID if applicable] | [Open / In progress / Closed]
| 1 | 03/21/2020 | Test of API connection was missed in QA, which meant that an issue with the connection was not picked up until go live. | Negative | None | Add a new test case for this test in QA environment | Request additional test case from test manager and inform PMO. | Project manager | 2.13.003 API connector | Closed
| 2 | 2020-03-05 | Agreeing the rating for defects in advance avoided facilitated meant that some 'cosmetic' issues could be fixed post go live. | Positive | Early in UAT issues that weren't blocking were logged as defects. | During project initiation agree and document how issues/defects will be rated, and define which issues ratings will not be blocking for go live. E.g. Defect - a function doesn't work - blocker for go live Cosmetic - no impact on function - nice to have - not blocker for go live. | Share lesson with PMO and suggest amended to the project initiation process. | Project manager | 3.1 UAT | In progress
[Notes
Every organisation has a different approach to the lessons learned log. This example includes all of the information that needs to captured,
and has been used on numerous real world projects. However, feel free to tweak this to fit your project.]
[Columns you might want to add:
|  | Project phase |  | The relevant phase e.g. initiation, build, test etc
|  | Recommended items to add to a process |  | Where the lesson requires an addition to a process note it here e.g. 'add end to end integration test to UAT phase'.
|  | Items to remove from a process |  | Note any items that need to be removed from a process e.g. 'for OOTB SaaS projects remove customisation design from build phase.'
|  | Closed date |  | The date when all actions related to the lessons learned are completed.
|  | Latest progress |  | A progress update e.g. 'sent lesson recommendations to PMO for review.'

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)