## Lessons Learned
Get Access to our Complete Collection of 40 Editable Google Doc/Sheet Lessons Learned Templates here.
LESSONS LEARNED LOG
Project Name: InfoNexus
Project Description: InfoNexus is an annual conference at McGill University run by the School of Information Studies students. Every year, it brings information specialists together in the city of Montreal to network and discuss various Information Studies topics.
Purpose: To identify and record lessons learned and future recommendations. This document is intended to collect information that has been learned during a phase of a project as well as the team's impressions of what worked well and what did not work well. This document should be updated throughout the entire lifecycle of a project and the results will be used to update or improve the overall process as appropriate.
Year | Entered by | Category | Issue Name | Problem or Success | Problem/Success Description | Impact | Recommendation | Outcome
2017 |  | Organizational | No Theme | Problem | After reviewing the surveys, there was a complaint that there was no clear theme chosen for InfoNexus 2017. | People were confused. There were speakers that were not relevant to some audience members. | Choose a theme for next year. |  | Example

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)

## Template Guide
Instructions for Lessons Learned
Field | Description
Year | Write the year of the InfoNexus Event. This is to keep track of when changes were made in order to see the progression of things. If for example we do not understand why a change was made, we can look at the years and track why decisions were taken at specific times.
Entered by | Who is the person inputting the data? If needed, this information will be used to ask the person more specifications and details on the lessons learned. However, if for any reason, a person prefers to remain anynonymous, they may do so, and simply write "Anonymous".
Category | This is for sorting purposes. There is a drop-down menu with a list of potential categories for the problems or successes. If there is a category to be added, it may be done by going on the "Data for Drop-Down Menus", and adding the name of the category to the list.
Issue Name | Create a name for this issue that is easily identifiable.
Problem or Success? | Is this a problem, a success or just a comment? The sole purpose of this column is to easily sort the situations by "problem", "success", or "other". "Other" could be a neutral comment about the event.
Problem/Success Description | Desscribe the problem or success in as much detail as possible.
Impact | Describe the impact this problem or success had on the event. For example, if the posters worked really well for marketing purposes, then we would write that "From the surveys, we see that one of the most popular ways people heard from the event is from the posters. This lead to an increase in attendance from people who weren't from the program but who were interested in Information Studies".
Recommendation | Describe the lesson learned and the corrective action taken or not taken. This is a suggested improvement area to prevent and/or avoid this issue next time. Be specific and watch using jargon/acronyms. If acronyms are used, document the entire word and/or meaning.
Outcome | When possible, when changes are made, the "future" team can observe their impact and write whether the changes worked or didn't work. For example. If the problem was that there was low attendance, we may suggest raffling prizes to attract attendees. If the following year, there was more attendance due to the prizes, then we would write that "There was an increase in attendance at this year's InfoNexus due to the raffle. People were explicitely excited about it and the surveys demonstrate that this idea was a success".

## Data for Drop-Down Menus
Data for Drop-Down Menus
How to: Below is the list of fields for the Lessons Learned sheet. Some of the fields require a drop-down menu with a list of terms for that field. This is done in order to avoid errors when sorting the data by keeping the information consistent. So for example, if there was no drop-down menu, people can accidentally write "markting" instead of "marketing" due to a typo. So, when sorting by "marketing", the data with "markting" won't show up. So, how to create a drop-down list?
1. In the Lessons Learned sheet, click on the first cell under the field in which you want a add a drop-down menu and select as many cells as needed.
2. On the main excel menu, click on the "Data" tab and look for "Data Validation".
3. In "Select", in "Validation Criteria", select "List".
4. In "Source" click the button next to the search bar, and select the list of terms you want to have appear in the drop-down menu.
5. Click "Ok" and you should be all set! If in the future, you want to add more terms, you can, and it will automatically appear in the drop-down list.
Year | Entered by | Category | Issue Name | Problem or Success | Problem/Success Description | Impact | Recommendation | Outcome
|  | Logistics | Other | Problem
|  | Website |  | Success
|  | Organizational |  | Other
Sponsors
Grants
Website
Marketing
Other