## Project Information
RACI Chart
Rule Chapter 74-1 does not require a RACI Chart. This is an FDOT Recommended tool.
Instructions |  | Project Information
1 | Fill out the Project Information beginning on Row 5 above. | Project | BI/DW
2 | Delete Rows 11-13 in the RACI Chart as these are for example-purposes only. | Project Manager | Lani Nash
3 | Identify the project tasks. Meet with key stakeholders to develop a list of project tasks. List the tasks needed in order to complete the project along each row in Column B on the RACI Chart. FDOT recommends highlighting alternating rows for easy reading. Insert or delete rows as needed. | Risk & Complexity Category | 2 (pre charter)
4 | List the Project Resources (names or job titles) involved in the process in each column along Row 9. Insert or delete columns as needed. | Project Sponsor | John Krause
5 | Assign an R, A, C, or I to finalize the matrix with who is Responsible, Accountable, Consulted, or Informed on each task. | Last Updated (Date) | 2017-05-15
6 | Log any updates to this template in the Update Log beginning on Row 11, Columns I & J of this tab. | Update Log | Purpose of the update
7 | If this template does not fit the needs of the project, specifically document in the Project Management Plan (PMP) that deviation from this template is necessary. Any altered, added or removed sections to the template must be approved by the signatories listed on the PMP template. Note: Any modifications to the approved template must still meet the requirements of Rule Chapter 74-1, Florida Administrative Code (F.A.C.). | 2017-01-03 | Just wanted to make an entry.
|  | 2017-02-21 | Added R005 and R006.
Definitions |  | 2017-03-29 | Escalated R003 to I001.
ACCOUNTABLE | The person who makes the final decision and has ultimate ownership of the work - This role cannot be delegated | 2017-04-25 | Entered CR001.
CONSULTED | The person who must be consulted before a decision or action is taken | 2017-05-15 | Documented LL001 and LL002.
Function | The task, critical decision, or activity needed in order to complete the project.
INFORMED | The person who must be informed that a decision or action has taken place
Project Resource | The individual (names or job titles) involved in the process to complete the project.
RESPONSIBLE | The person who is assigned to do the work - Responsibility can be delegated

## RACI Chart
RACI Chart
| Project | BI/DW | [5 empty] | Sponsor |  | John Krause
| Project Manager | Lani Nash | [5 empty] | Worksheet Updated |  | 2017-05-15
| R&C Category | 2 (pre charter)
| R | Who is RESPONSIBLE |  |  |  | The person who is assigned to do the work - Responsibility can be delegated | [7 empty] | Usually 1
| A | Who is ACCOUNTABLE |  |  |  | The person who makes the final decision and has ultimate ownership of the work - This role cannot be delegated | [7 empty] | Usually 1
| C | Who is CONSULTED |  |  |  | The person who must be consulted before a decision or action is taken | [7 empty] | May be multiple
| I | Who is INFORMED |  |  |  | The person who must be informed that a decision or action has taken place | [7 empty] | May be multiple
| Tasks | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource | Project Resource
|  | Sponsor | Steering Committee |  |  |  |  | Project Manager | PM Support | Team Leads | [5 empty] | SME's |  |  |  |  | Vendor
Example | Business Requirements Document | R | A | R | C / I | R
| Monitor & Update Spend Plan | R | C |  | C / I
| Develop Communications Plan | A | C | R | C / I
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task