## Lessons Learned Template
Get Access to our Complete Collection of 40 Editable Google Doc/Sheet Lessons Learned Templates here.
Lessons Learned Template
Today's Date: | 2023-01-02
Project Name: | My Project
Project Manager: | George Washington
Notes: | (add any extra info here)
| WIN or ISSUE | Describe What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items
| WIN | We implemented a new time tracking system with the team to test whether or not productivity would improve | We saved 200 hours of time and delivered the work 2 weeks early | We will roll out time tracking to all teams in the company | 1. Purchase software licenses for all employees 2. Send email explaining why time tracking is necessary
| ISSUE | Our IT manager for the project was out sick for 2 weeks and there was no available replacement, so we had to wait for her return | The project was delayed 4 weeks and the client was upset. A $25,000 credit was issued to the client | We need to have redundancy in the IT department to ensure there is always someone available | Chat with CEO and HR about hiring additional IT help
| WIN | The client was so happy with the final presentation that she offered us a 2 year exclusive contract! | This contract is going to double our revenue growth over the next 2 years | The new style of in-person client presentation should be used on more projects, when possible. | Share the new client presentation format with other teams

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)

## Template Guide
How to Use Our Lessons Learned Template
The lessons learned template is a tool to note what worked and what didn't in your project to repeat the positive and avoid the negative.
Today's Date: Enter today’s date
Project Name: Give your project a name, so it can be quickly identified
Project Manager: Enter the name of the person overseeing the project. This could be a proper project manager or any staff member who is the owner of the work.
Notes: This field is for you to add any relevant information you’d like. Ideas: client name, stakeholders, project summary, budget, etc.
WIN or ISSUE: Choose either WIN or ISSUE to classify the lesson. A win is something positive that happened, and an issue is something negative that happened
Describe What Happened: Use this field to give a detailed description of the lesson you learned
What Was the Impact?: Here, you’ll describe the positive or negative result, and the impact there may have been. For a win, write about the positive outcome that occurred. For an issue, write about the negative consequences you experienced due to the problem
How Does This Change Future Projects?: In this field, record your thoughts on how this lesson might impact future work. Think about how other people in your organization might benefit from learning this lesson
Action Items: Add the actionable steps that will be taken to address your win or issue. Every row should have an action item, even if it is as simple as “monitor to see if it happens again.” This is the most important part of the template, because you are outlining the steps you will take to improve