## Foreword
Get Access to our Complete Collection of 40 Editable Google Doc/Sheet Lessons Learned Templates here.
Template: Lessons learned tracking sheet
Foreword
Developing a mature financial statements process is an iterative process. It is important to take time at the end of each cycle to consider what went well and what could be improved. This tracking sheet helps finance teams to communicate the issues and challenges from the previous financial statement process and document the proposed solutions for implementation. Lessons learned in progress A tracking sheet, such as this one, allows the team to record what didn't go to plan and track the progress of improvements. Completed lessons learned This is register for keeping track of completed items from previous year's lessons. It is important to keep a record of past items as a reference as this assists in the publication of position papers and supporting information for future decisions. Positive lessons It is helpful to keep track of the positive lessons in addition to negative lessons.

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)

## Lessons learned in progress
Financial statements
Lessons learned in progress tracking sheet
Ref | Key topic | Identified issue | Proposed resolution | Action assigned to | Progress to audit committee | Internal only | Status | Planned completion | Actual completion | Feedback/comments
Lessons learned identified in 20x1 - 20x2 financial year
1 | Financial statements model | The Model didn't detect several internal consistency errors that the auditors picked up. | - Review internal consistency functionality and ensure it is working | Financial statements | No | Yes | In progress | Hard close |  |  | 1
2 | Supplimentary reporting pack | Supporting documentation for the supplimentary reporting packs wasn't compelted untill just before sign-off which resulted in a late submission | #ERROR! | Financial statements | Yes | No | Not started | Hard close |  |  | 1
3 | [10 empty] | 1
4 | [10 empty] | 1
5 | [10 empty] | 1
6 | [10 empty] | 1
Lessons Learned identified in 2014 - 2015 Financial Year
1 | [10 empty] | 1
2
3
4
5
Lessons learned to continue on a regular basis
1 | [10 empty] | 1
2 | [10 empty] | 1
3 | [10 empty] | 1
4 | [10 empty] | 1
5 | [10 empty] | 1

## Completed lessons learned
Financial statements
Completed lessons learned tracking sheet
Ref | Key topic | Identified issue | Proposed resolution | Action assigned to | Progress to audit committee | Internal only | Status | Planned completion | Actual completion | Feedback/comments
Lessons learned identified in 2019 - 2020 financial year - COMPLETED
1 | External assurance | There was not enough time to act upon the external assurance feedback of hardclose before the year end began. | - Ensure the external assurance provider is arranged to start earlier - Ensure the that feed back is released incrimentally rather than entire document at the end | Financial statements | Yes | No | Completed | 2020-11-28 | 2020-12-08 | Met with the external assurance provider to discuss timing issue and arranged for them to come in the tail end of the process to begin assurance work before finalisation of the entire process. | 1
2 | [10 empty] | 1
3 | [10 empty] | 1
4 | [10 empty] | 1
5 | [10 empty] | 1
6 | [10 empty] | 1
7 | [10 empty] | 1
8 | [10 empty] | 1
9 | [10 empty] | 1
10 | [10 empty] | 1
11 | [10 empty] | 1
12 | [10 empty] | 1
13 | [10 empty] | 1
14 | [10 empty] | 1
15 | [10 empty] | 1
16 | [10 empty] | 1
17 | [10 empty] | 1
18 | [10 empty] | 1
19 | [10 empty] | 1

## Positive lessons
2019-20 Financial Statements
Positive Lessons
Ref | Key topic | Identified issue
1 | ANAO | While the Audit Protcals where not formally signed off they set clear expectations of all stakeholders
2 | Process | Monthly and Annual Special Account Sign-off pack allowed for easy supporting data for the special account note
3 | Project plan | Project Plan allowed easy tracking for management on the progress of the financial statements and allowed them to reallocated resources where pressures where building
4
5
6
7
8
9
10
11
12
13
14
15
16
17

## Metadata (hidden)
Raw data
Section | Yes/No | Status
Accounts payable team | Yes | Not started
Accounts receivable team | No | In progress
External budgets |  | Issues
Financial statements |  | Completed
All |  | Overdue